## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Gyana | 2026-08-26 | Judge agents returned stub 0.0 scores with 'Not yet implemented' — expected during scaffold phase, not a real defect, but tracked for visibility. | Sprint 1 | Gyana | Logical | Implemented real Gemini-based scoring for all 4 judge agents with structured JSON prompts. | 2026-08-26 | Closed | Resolved as part of planned Milestone 1 work.
2 | Gyana | 2026-08-27 | Completeness agent returned 'Evaluation failed due to an internal error' when tested via Swagger UI on a real multi-agent request. | Sprint 1 | Gyana | Logical | Root cause suspected as Gemini free-tier rate limiting (4 sequential LLM calls per request). Added retry logic with exponential backoff (2s/4s/8s) in LLMClient. | 2026-08-27 | Closed | Confirmed fixed after retest — all 11 tests passing, no further internal errors observed in that session.
3 | Gyana | 2026-09-02 | Demo UI at '/' returned 404 Not Found after adding app/static/index.html and mounting StaticFiles in main.py. | Sprint 2 | Gyana | Standards | Root cause was browser cache / uvicorn --reload not having restarted before test. Confirmed working after restart and hard refresh. | 2026-09-02 | Closed | No code change needed — deployment/reload timing issue.
4 | Gyana | 2026-09-02 | Retrieval returned zero evidence for a well-covered question (capital of France). Diagnostic script (test_retrieval.py) showed ChromaDB attempting to download its own bundled ONNX embedding model from Chroma's CDN, timing out after 9+ minutes on a slow connection, instead of using the configured sentence-transformers model. | Sprint 2 | Gyana | Logical | Root cause: Chroma's embedding_function was not reliably persisted/reused on collection reload, causing fallback to Chroma's default embedder. Fix: VectorStore now computes embeddings explicitly via sentence-transformers and passes raw vectors to Chroma (add/query), removing dependency on Chroma's internal embedding_function entirely. | 2026-09-02 | Open - pending retest on Gyana's machine | High priority - this silently degraded the RAG pipeline (judges were falling back to the LLM's own knowledge instead of retrieved evidence) without raising an error.
5 | Gyana | 2026-09-10 | Gemini free-tier RPM limit (15 requests/min) hit during M2.4 validation suite run, in addition to a separate daily quota exhaustion on gemini-3.7-flash (20/day). | Sprint 3 | Gyana | Configuration/Logical | Switched LLM_MODEL to gemini-2.0-flash-lite (1500/day free tier). Optimized run_validation_suite.py to skip unnecessary Accuracy calls for irrelevant/off-topic cases (24->22 calls) and added configurable delay between calls. Updated LLMClient to parse Gemini's actual retry_delay from 429 errors instead of blind exponential backoff. | 2026-09-10 | Closed | Confirmed fixed - validation suite completed successfully with 0/22 mismatches.
6 | Gyana | 2026-09-10 | M2.4 validation run found 3 prompt-quality mismatches: (1) Accuracy agent classified a multi-claim response as 'incorrect' when it should be 'partially_correct' since one claim was right; (2) Relevance agent had no clear distinction between 'unrelated' and 'off_topic' categories; (3) Hallucination agent flagged an off-topic response as having unsupported claims when it wasn't attempting to answer the question at all. | Sprint 3 | Gyana | Logical (prompt design) | Rewrote Accuracy prompt with explicit multi-claim partial-correctness rule and example. Rewrote Relevance prompt with explicit unrelated-vs-off_topic definitions and examples. Rewrote Hallucination prompt to first check whether the response attempts to answer the question before evaluating claims for support. | 2026-09-10 | Closed | Re-ran validation suite after fix: 0/22 mismatches, confirmed resolved.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others